## Sheet1
sl# | Project | Customer | Activities | Hardware | Activity Owner | owner | owner 2 | AE | remarks | dependencies | Status | Final Date
1 | FTM | Minda | Flasher | Jlink plus | Sushmitha | Sushmitha | Anusha | Vivek |  |  | Completed
|  |  | CAN | PCAN | Sushmitha | Sushmitha | Anusha | Vivek |  |  | Completed
|  |  | Picoscope | 3203D | Sushmitha | Sushmitha | Anusha | Vivek |  |  | Completed
|  |  | DMM | GW-instek GDM-9061 | Sushmitha | Sushmitha | Anusha | Vivek |  |  | Completed
|  |  | Printer | Zebra | Venkat | Sushmitha | Anusha | Vivek | Barcode details |  | Completed
|  |  | Handheld scanner | Honeywell | Venkat | Sushmitha | Anusha | Vivek |  |  | Completed
|  |  | MTS.TEST.0001.v1.0.0 |  | Manik | Sushmitha | Anusha | Vivek |  |  | Completed
2 | FCT for EL PDU | Ather | Electronic load | ITECH-IT-8513C+ | Prithvisha | Anusha | Manik | Annesh | Samples,Sweep | Device not available | Completed | 2025-02-01
|  |  | pps | TTI -CPX400DP | Prithvisha | Anusha | Manik | Annesh | Sweep | Sweep | Completed | 2025-02-01
|  |  | Fixed scanner | Keyance SRX100 | Anusha | Anusha | Manik | Annesh |  | Device not available | Completed | 2025-02-01
|  |  | MTS------------- |  | Manik | Anusha | Manik | Annesh |  |  | Completed | 2025-02-01
3 | Ageing and Vibration Test for the Instruments Cluster | Aumovio | Fixed Scanner | Keyance | Venkat | Sneha | Pradeep | Annesh |  | Device not available | not started | 2025-02-01
|  |  | CAN |  | Sneha | Sneha | Pradeep | Annesh | information required |  | Inprogress | 2025-01-25
|  |  | Vibration instrument |  |  | Sneha | Pradeep | Annesh |  |  | Inprogress | 2025-01-25
|  |  | MTS------------- |  | Pradeep | Sneha | Pradeep | Annesh | Information regarding storing data to MES |  | Inprogress | 2025-01-25
4 | TG Wireless Power Charger -EOL | Minda | Flasher(1) | PE Micro | Sushmitha | Venkat&Sushmitha | Manik | Vivek | Flashing files | Details are needed | Completed | 2025-01-12
|  |  | UART flashing(1,3,6) |  | Sushmitha | Venkat&Sushmitha | Manik | Vivek |  | Bench setup required, UART software | Completed | 2025-01-12
|  |  | Fixed scanner(1,2,3,4,5,6) |  | Venkat | Venkat&Sushmitha | Manik | Vivek |  | Device not available | not started | 2025-01-12
|  |  | Robot communication(2,4) |  | Sneha | Venkat&Sushmitha | Manik | Vivek |  | Device not available | not started | 2025-01-12
|  |  | pps(3,6,7) |  | Prithvisha | Venkat&Sushmitha | Manik | Vivek | Sweep |  | Completed | 2025-01-12
|  |  | UART Calibration(3) |  | Sushmitha | Venkat&Sushmitha | Manik | Vivek | UART Baudrate and calibration commands to check calibration status and to write date and serial number |  | Completed | 2025-01-12
|  |  | Printer(3,6) |  | Venkat | Venkat&Sushmitha | Manik | Vivek | Details of barcode | Details of barcode | Inprogress | 2025-01-12
|  |  | Screw Driver(5) |  | Sneha | Venkat&Sushmitha | Manik | Vivek | Make model | Device not available | not started | 2025-01-12
|  |  | Handled scanner(5) |  | Venkat | Venkat&Sushmitha | Manik | Vivek |  | Device not available | not started | 2025-01-12
|  |  | Dmm(6) |  | Prithvisha | Venkat&Sushmitha | Manik | Vivek |  |  | Completed | 2025-01-12
|  |  | Vision sensor/LED analyser(6) |  | Pradeep | Venkat&Sushmitha | Manik | Vivek | Make model | Make model | inprogress | 2025-01-12
|  |  | Traceability | [8 empty] | 2025-01-12
5 | Assembly & Test line for WLC_YXA-MC | Minda | Fixed scanner(1)(2)(3)(4)(5)(6)(7)(8) | Keyance | Anusha | Anusha and Sneha | Manik | Tarun |  |  |  | 2025-01-12
|  |  | Screw driver(2)(5) | Hantas /kolver | Sneha | Anusha and Sneha | Manik | Tarun |  | make model |  | 2025-01-12
|  |  | Camera(2)(5)(6) | keyance | Pradeep | Anusha and Sneha | Manik | Tarun |  |  |  | 2025-01-12
|  |  | UART(4) |  | Prithvisha | Anusha and Sneha | Manik | Tarun |  | UART Baudrate and calibration commands |  | 2025-01-12
|  |  | PPS(4)(6)(8) | GWI | Prithvisha | Anusha and Sneha | Manik | Tarun |  | sweep |  | 2025-01-12
|  |  | CAN(4)(6)(7)(8) | PCAN | Sneha | Anusha and Sneha | Manik | Tarun |  | DBC file |  | 2025-01-12
|  |  | Printer(6) |  | Anusha | Anusha and Sneha | Manik | Tarun |  | Barcode details |  | 2025-01-12
|  |  | DMM | GWI | Prithvisha | Anusha and Sneha | Manik | Tarun |  |  |  | 2025-01-12
|  |  | Vision sensor/LED analyser(6) | Keyance | Pradeep | Anusha and Sneha | Manik | Tarun |  | make model |  | 2025-01-12
|  |  | Face recognization device(8) |  | Anusha | Anusha and Sneha | Manik | Tarun |  |  |  | 2025-01-12
|  |  | Traceability |  | Manik | Manik | Manik | Tarun |  |  |  | 2025-01-12
2025-01-12
6 | FTM for TML Sierra | Minda | Flasher | Jlink plus | Sushmitha | Sushmitha | Anusha | Vivek
|  |  | CAN | PCAN | Sushmitha | Sushmitha | Anusha | Vivek
|  |  | Picoscope | 3203D | Sushmitha | Sushmitha | Anusha | Vivek
|  |  | DMM | GW-instek GDM-9061 | Sushmitha | Sushmitha | Anusha | Vivek
|  |  | Printer | Zebra | Venkat | Sushmitha | Anusha | Vivek
|  |  | Handheld scanner | Honeywell | Venkat | Sushmitha | Anusha | Vivek
|  |  | MTS.TEST.0001.v1.0.0 |  | Manik | Sushmitha | Anusha | Vivek
7 | Traceability for Y17 HV CPRSR & Y17 HV UNDERFLOOR | Yazaki | Traceability |  | Manik | Manik&Sreerag | Venkat | Adithya | Mater data and barcode content
8 | Hella OBC | Hella | Scanner - Cognex - DMR152S |  | Venkat | Sneha | Prithvisha | Adithya
|  |  | CAN- National Instruments - 8502(UDS) |  | Sneha | Sneha | Prithvisha | Adithya
|  |  | PLC |  | SaiThilak | Sneha | Prithvisha | Adithya
|  |  | HIPOTTester- MicroTest7631 |  | Prithvisha | Sneha | Prithvisha | Adithya
|  |  | NI DIO ToolMonitor |  | Anusha | Sneha | Prithvisha | Adithya
|  |  | I-TAC |  | Manik | Sneha | Prithvisha | Adithya
|  |  | Power meter Yokogawa-Wt310 |  | Prithvisha | Sneha | Prithvisha | Adithya | Efficiency details
|  |  | PPS -ITECHIT6005C |  | Prithvisha | Sneha | Prithvisha | Adithya | part required
|  |  | Yokogava powermeter |  | Prithvisha | Sneha | Prithvisha | Adithya | Variant addition details
|  |  | GW-instek-pps |  | Prithvisha | Sneha | Prithvisha | Adithya
|  |  | Printer |  | Venkat | Sneha | Prithvisha | Adithya | Barcode details
9 | BCON | Lumax | Master data validation |  | Pradeep
|  |  | cycle time reduction |  | Sushmitha & Sneha
|  |  | Deviation for each axis is coming around -1.5 dBm to - 2.0 dBm to every time, where as in NIDEC it is within -0.5 dBm. A step by step analysis on correction value and hardware noise to be done and early fix is required to resolve the issue before MPP |  | Sushmitha and Sachith
|  |  | How to run mass production training |  | Pradeep
10 | EOL for WCM M&M | Minda | Barcode Scanner - Fixed | Symbol/Zebra | Anusha | Sneha | Prithvisha | Adithya |  |  | not started
|  |  | Scara Robot with Controller | MAKE-Epson , PART NO-T3 | Sneha | Sneha | Prithvisha | Adithya |  |  | not started
|  |  | PPS | - GW-Instek -GPP-2323 | Sneha | Sneha | Prithvisha | Adithya |  |  | not started
|  |  | DMM | MAKE-GW-Instek, PART NO-GDM-8261A | Sneha | Sneha | Prithvisha | Adithya |  |  | not started
|  |  | DC Electronic Load | MAKE- BKP, PART NO-8061 | Sneha | Sneha | Prithvisha | Adithya |  |  | not started
|  |  | CAN Transciever | MAKE- NI ,PART NO-USB-8502 | Sneha | Sneha | Prithvisha | Adithya |  |  | not started
|  |  | Printer |  | Anusha | Sneha | Prithvisha | Adithya |  |  | not started
|  |  | MTS.TEST.0001.v1.0.0 |  | Pradeep | Sneha | Prithvisha | Adithya |  |  | not started
12 | FTM for WCM_M&M-1 & 2 | Minda | PPS |  | Sushmitha | Sushmitha | Anusha | Vivek |  |  | not started
|  |  | DMM |  | Sushmitha | Sushmitha | Anusha | Vivek |  |  | not started
|  |  | CAN Communication |  | Sushmitha | Sushmitha | Anusha | Vivek |  |  | not started
|  |  | Flasher |  | Sushmitha | Sushmitha | Anusha | Vivek |  |  | not started
|  |  | UART |  | Sushmitha | Sushmitha | Anusha | Vivek |  |  | not started
|  |  | Oscilloscope |  | Sushmitha | Sushmitha | Anusha | Vivek |  |  | not started
|  |  | MTS.TEST.0001.v1.0.0 |  | Manik | Sushmitha | Anusha | Vivek |  |  | not started
11 | FTM for WCM_YXA MCA-2 | Minda | Flasher | Jlink plus | Sushmitha | Sushmitha | Anusha | Vivek |  |  | not started
|  |  | CAN | PCAN | Sushmitha | Sushmitha | Anusha | Vivek |  |  | not started
|  |  | Picoscope | 3203D | Sushmitha | Sushmitha | Anusha | Vivek |  |  | not started
|  |  | DMM | GW-instek GDM-9061 | Sushmitha | Sushmitha | Anusha | Vivek |  |  | not started
|  |  | Printer | Zebra | Venkat | Sushmitha | Anusha | Vivek |  |  | not started
|  |  | Handheld scanner | Honeywell | Venkat | Sushmitha | Anusha | Vivek |  |  | not started
|  |  | MTS.TEST.0001.v1.0.0 |  | Manik | Sushmitha | Anusha | Vivek |  |  | not started